## Admin Web App Features
Admin Web App
Feature Item | Efforts | Status
System Security
SignUp / Register User Mobile Number Verification: Send OTP thru SMS. (Mandatory) Email Verification: Send OTP thru Email. (Mandatory) |  | Completed
OTP Validation Screen |  | Completed
Login Screen |  | Completed
Forgot Password
Dashboards for Admin
Admin Dashboard with Various blocks and Statistics as required
User Management
Add User from Admin side Admin will add multiple user like Faculty/Team member and executive management from variuos department according to their acess criteria . |  | Completed
List of users Admin can view all the user with their department. This list will have all required filters such as Show Role wise users, status wise users, department wise, etc List will have bulk user update facility. |  | Completed
Edit user |  | Completed
Delete user If user has some transactions in the system, that user can't be deleted. |  | Completed
Block user Admin can block a single user or multiple users at a time. Blocked users can not login to system. |  | Completed
Activate user Admin can activate the blocked user |  | Completed
Search User |  | Completed
Notification Module
Create Templates for Mail, SMS & InAPP Notifications |  | Completed
List of all Notification Templates for Mail, SMS & InAPP |  | Completed
Edit & Delete Facility of all Notification Templates |  | Completed
SMS Gateway Integration for Text Messages |  | We will do it later
In-App Notification Display after User Login
Eventwise Notifications to be sent to user using templates Assuming 10 Events |  | We will do it later
System Setting
Company Basic info & Logo |  | Completed
Company Locations |  | Completed
Bank Details |  | Completed
Tax Info |  | Completed
Payment Gateway Configuration Keys
SMS Gateway Configuration Keys
Amazon S3 Configuration Keys
Corporate Client Management
Add New Client |  | Complete
List of Clients |  | Complete
Edit / Delete of Clients |  | Complete
Create Login functionality to Corporate Admin |  | Complete
Add multiple locations for each client |  | Complete
Corporate Contract Management
Add Contract Information & Rates |  | Complete
List of all Contracts |  | Complete
Edit & Delete of the Contracts |  | Complete
Highlight the contract 1 month before expiry & Send Notification to Corporate Admin
Contract Renewal Mechanism
Notification goes to Corporate Admin on Renewal of Contract
Vendor Management
Add New Vendor |  | Complete
List of Vendors |  | Complete
Edit / Delete of Vendors |  | Complete
Create Login functionality to Vendor |  | Complete
Filter Vendor by City, Type & Vendor Status |  | Complete
Driver Management
Add New Driver |  | Complete
List of Drivers With filters as Active, Inactive, Suspended, |  | Complete
Edit / Delete of Driver |  | Complete
Search Driver by Name, Phone number |  | Complete
Create Login functionality to Driver |  | Complete
Filter Driver by City, Status |  | Complete
List of Cars Registered by Vendor With filters as Car Category/Type, Status of Insurance, PUC, etc |  | Complete
Master Data
Car Category Management
Add Car Categories |  | Complete
List of Car Categories |  | Complete
Edit / Delete Facility of Car Categories |  | Complete
Search Car Category by Category Name |  | Complete
Filter Car Category by Category Type |  | Complete
Fare Management This needs thorough discussion, as I can imagine this is going to be very complex module.
Create New Standard Fare Rates As per Car Category, Per Km Rate, Time, Minimum Km & Other parameters
List of all Fare Rates
Edit & Delete of Fares
Facility to Change the Fares as per Corporates
Facility to Change the Fares as per Vendors
Document Validations Need more discussion on this section
List of all Documents Filter with Pending for Validation, Validated, Need More Info
Facility to Change the Status of each document
Booking Management There a lot more in this module for Digigo Admin than these features. Need to Discus thoroughly.
List of all Trips Bookings (Filter with Corporate, Vendor, Car Type, Date, Month, etc)
Facility to make any change / status of the Trip booking.
Admin List of Rejected Vendor Trips. Facility to rebroadcast the Trip to another Vendor
Admin can also Cancel the Trip Notification goes to User & Corporate Admin
Tracking Module
Admin can track the trip on Web App
Facility to extend this Module to any other User for Any Trip
Feedback Management
List of all feedbacks sent by Client
Reply to the feedback
Reporting System
All Bookings Report Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Corporates, Vendors, Car Category, Origin City, Status: Upcoming, Completed, Cancelled by User, Cancelled by Vendor
Vendor wise Bookings Report Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Accepted by Vendor, Rejected, Cancelled, Completed
All Corporate Bills Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Status : Paid/Pending
All Vendor Bills Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Status : Paid/Pending
User Registration Report Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Corporate, Vendor
Corporate Reports Filters with Status: Active/Inactive, Rides Requested/Completed/Cancelled/Rejected, Number of Employees Registered, Current Usage, Pending Bill Amount, Settled Bill Amount
Billing Unit
Here we have to lots of brainstorming. So Here we assume some standard efforts for costing purpose. After detailed brainstorming, we will readjust the efforts.
Graphic Design
Requirement Analysis, Database Design & System Architecture
BRD, FSD Documentation
Total Development Efforts (In Person Days)

## Corporate Admin Web App
Corporate Admin Web App Features
Feature Item | Efforts | Status
Corporates Activities
Show a separate section on Dashboard for Admin.
Corporate Admin Menubar
User Management
Create New Employee Form
List of all Employees with Filter Role, Manager Name, Department, City, Search Employee
Edit / Delete Facility
Corporate Heirarchy List
Tracking Module
List of Trips with Date wise & statuswise filters
Track The Ongoing Trips
See the Map Routes of Completed Trips
Billing Section
List of all bookings with following filters Status: New, Approved, Rejected, Cancelled Employee wise, From Date, To Date, Month
List of all Bills with filters Pending / Unpaid, Paid
View of Individual GST Bill for each Trip, Download as PDF, Print
Facility to make Individual Bill Payment or Bulk Invoice Payments
TDS Deduction Facility
Payment Gateway Integration (Hosted Gateway)
On Success Payment, Show Payment Receipt with Amount, Date, Invoices paid, etc
On Failure of Payment, Show Failure Message
Payment History with TDS Deducted & GST Paid
Reporting System
Summary & Detail Reports of Consolidated Bill Daily, Weekly, Monthly, Yearly, Custom Period Filter: Manager, Employee, Search Facility: Name, Employee ID
Summary & Detail Reports of Reimbursements Daily, Weekly, Monthly, Yearly, Custom Period Filter: Manager, Employee, Search Facility: Name, Employee ID |  |  | Daily | Weekly | Monthly | Yearly | Custom Period
View of Individual Reimbursement, Download as PDF, Print
Facility to convert Status of Reimbursement into Paid. |  |  |  |  | Dec 2019
Contract Management |  |  | Select Manager |  |  | Select Employee
List of Annual Contracts |  |  | All |  |  | All
Detailed view of each Contract Page
Requirement Analysis, Database Design & System Architecture
BRD, FSD Documentation
Graphic Design of Mobile App (Two options) |  |  |  |  | 5000
Total Development Efforts (In Person Days) |  |  |  | 18% | 900

## Corporate Emp-Mangr Web App
Employee & Manager Web App & Mobile App Features
Feature Item | Efforts | Status
Login / Registration
Login Screen
Forgot Password
OTP Validation Screen
User Signup - Not Allowed. As Corporate Admin will generate the User IDs
User Profile (Common to all Roles)
Create Profile (Select reporting manager & department)
View User Profile
Reporting Manager will Approve The Profile
Employee allocated Budget & Car Type/category
Edit User Profile
Reset Password Facility
Notifications (Common to all Roles)
Notifications bell icon with the number of new notifications
When clicked on bell icon, show all notifications in Read & unread format
When clicked on any notification, user is redirected to that transaction.
Trip Booking
User Dashboard
User Menubar
Trip Booking Form - Create New Trip Add Pickup Address, City and Destination Address,City, Date & Time, Trip Type(Round Trip, One Way, Hourly Package, City Tour, Airport pickup/drop).
Display Estimated Cost = Distance x Rate + Toll + Parking + Driver Allowance
Trip Details Page
Manager Approval or Rejection Notification and Status update on trip details page If immeidate approval authority is not available, employee can select other Approving Authority.
Vendor Approval or Rejection Status Update & Notification
My Bookings (History)
Edit & Delete Facility
Facility to Cancel the Trip
Travel Reimbursement
Trip Journey
Status Update on Trip View Page when Driver starts the trip from Garage.
User share the Trip Code to identify Driver on Trip Strat Screen.
When Trip ends, Show all details like, Start Meter Reading, End Reading, Total KM Travelled, Total Bill, Entire Route. Need More discussion for this - at the time of Billing Module.
Trip Details Saved for Future use in Trip History & Tracking Google Map
Trip Feedback
Feedback Form with Rating for Driver & Car
List of all Feedbacks
Feedback Remark from Admin
Manager Section
Dashboard will have "Approval" section, visible only for Manager. A Count of new Bookings will appear on this section.
List of all bookings with following filters Status: New, Approved, Rejected, Cancelled Employee wise, From Date, To Date, Month
Facility to Approve, Reject the Booking
Notification goes to Employee, Digigo Admin, & all vendors in that city.
Manager can track any trip of his employees
Manager gets notification when Employee books a car better than his allocated category.
Requirement Analysis, Database & System Architecture
BRD, FSD Documentation
Graphic Design of Mobile App (Two options)
Total Development Efforts (In Person Days)

## Corporate Emp-Mangr Mobile App
Employee & Manager Web App & Mobile App Features
Feature Item | Efforts | Status
Login / Registration
Login Screen
Forgot Password
OTP Validation Screen
User Signup - Not Allowed. As Corporate Admin will generate the User IDs
User Profile (Common to all Roles)
Create Profile (Select reporting manager & department)
View User Profile
Reporting Manager will Approve The Profile
Employee allocated Budget & Car Type/category
Edit User Profile
Reset Password Facility
Notifications (Common to all Roles)
Notifications bell icon with the number of new notifications
When clicked on bell icon, show all notifications in Read & unread format
When clicked on any notification, user is redirected to that transaction.
Trip Booking
User Dashboard
User Menubar
Trip Booking Form - Create New Trip Add Pickup Address, City and Destination Address,City, Date & Time, Trip Type(Round Trip, One Way, Hourly Package, City Tour, Airport pickup/drop).
Display Estimated Cost = Distance x Rate + Toll + Parking + Driver Allowance
Trip Details Page
Manager Approval or Rejection Notification and Status update on trip details page If immeidate approval authority is not available, employee can select other Approving Authority.
Vendor Approval or Rejection Status Update & Notification
My Bookings (History)
Edit & Delete Facility
Facility to Cancel the Trip
Travel Reimbursement
Trip Journey
Status Update on Trip View Page when Driver starts the trip from Garage.
User share the Trip Code to identify Driver on Trip Strat Screen.
When Trip ends, Show all details like, Start Meter Reading, End Reading, Total KM Travelled, Total Bill, Entire Route. Need More discussion for this - at the time of Billing Module.
Trip Details Saved for Future use in Trip History & Tracking Google Map
Trip Feedback
Feedback Form with Rating for Driver & Car
List of all Feedbacks
Feedback Remark from Admin
Manager Section
Dashboard will have "Approval" section, visible only for Manager. A Count of new Bookings will appear on this section.
List of all bookings with following filters Status: New, Approved, Rejected, Cancelled Employee wise, From Date, To Date, Month
Facility to Approve, Reject the Booking
Notification goes to Employee, Digigo Admin, & all vendors in that city.
Manager can track any trip of his employees
Manager gets notification when Employee books a car better than his allocated category.
Panic Button
This section needs lots of brainstorming to understand what needs to be done when this button is pressed. This needs to be revisit after a thorough discussion. Efforts may vary that time. At this moment, we take some standard guess.
Requirement Analysis, Database & System Architecture
BRD, FSD Documentation
Graphic Design of Mobile App (Two options)
Total Development Efforts (In Person Days)

## Vendor-WebApp
DigiGo Mobile App Features
Feature Item | Efforts | Status
System Security
Login Form |  | Complete
Sign Up Form |  | Complete
Forgot Password |  | Complete
OTP Validation |  | Complete
Vendor Profile
Display Form only on First Login until it is completely filled
Add all Vendor Details, Upload KYC Documents, Agreement & Photo
Profile View Page
Edit & Delete
Driver List
List of all Drivers with filter of Active / Inactive / Removed
Driver Profile page. Vendor can see all documents submitted by Driver.
Facility to Approve, Reject the Driver Profile.
Facility to make Driver Active / Inactive
Fleet Master
Facility to enter Fleet or Cars details as per the Car Type & Car Make/model Master. All Car details, along with Permit documents, Insurance document, PUC document, FastTag & Registration Card.
List of All Cars with filters Car Type, Make, Model Highlight the car for expiring documents.
Edit & Delete Facility
Search facility by Car Name, Number,
Download as Excel Facility
Trip Booking
Vendor Dashboard
Vendor Menubar
List of All Bookings with Filters (New, Completed, User Cancelled, Vendor Cancelled, Vendor Rejected) Vendor can accept or Reject the booking.
When Vendor accept the booking, he see the list of cars to select and then list of Drivers to select.
Notification with Car + Driver Details goes to Corporate User, Corporate Admin, Digi-Go Admin & Driver
Modify the Car & Driver details for a trip, ONLY before the Trips starts. After this modification, again Notification with Car + Driver Details goes to Corporate User, Corporate Admin, Digi-Go Admin & Driver
When Vendor Cancels the Trip, Notification goes to Digigo Admin Only.
Trip Journey
User, Vendor & Digigo Admin (No SMS) gets notification when Driver starts trip from Garage
Vendor & Digigo Admin (No SMS) gets notification and status update on Trip details page when Trip Code is Shared by User to Driver & Trip Starts.
Vendor can track the trip on Mobile App
Vendor & Digigo Admin (No SMS) gets notification when Trip Ends
Save Trip Details & Tracking Route for Future use. Display the Trip details on demand when clicked on a Trip
Reporting System
List of all Invoices raised so far by Digigo. Filter all these invoices by Date, Car, Driver, Paid/Unpaid, Origin City.
Settlement Report (Date, Car, Driver, Paid/Unpaid)
Trip Report (Date, Car, Driver, Status: Completed, Cancelled)
Earning Report
Requirement Analysis, Database & System Architecture
BRD, FSD Documentation
Graphic Design of Mobile App (Two options)
Total Development Efforts (In Person Days)

## Vendor-Mobile App
Vendor Mobile App Features
Feature Item | Efforts | Status
System Security
Login Form
Sign Up Form
Forgot Password
OTP Validation
Vendor Profile
Display Form only on First Login until it is completely filled
Add all Vendor Details, Upload KYC Documents, Agreement & Photo
Profile View Page
Edit & Delete
Driver List
List of all Drivers with filter of Active / Inactive / Removed
Driver Profile page. Vendor can see all documents submitted by Driver.
Facility to Approve, Reject the Driver Profile.
Facility to make Driver Active / Inactive
Fleet Master
Facility to enter Fleet or Cars details as per the Car Type & Car Make/model Master. All Car details, along with Permit documents, Insurance document, PUC document, FastTag & Registration Card.
List of All Cars with filters Car Type, Make, Model Highlight the car for expiring documents.
Edit & Delete Facility
Search facility by Car Name, Number,
Download as Excel Facility
Trip Booking
Vendor Dashboard
Vendor Menubar
List of All Bookings with Filters (New, Completed, User Cancelled, Vendor Cancelled, Vendor Rejected) Vendor can accept or Reject the booking.
When Vendor accept the booking, he see the list of cars to select and then list of Drivers to select.
Notification with Car + Driver Details goes to Corporate User, Corporate Admin, Digi-Go Admin & Driver
Modify the Car & Driver details for a trip, ONLY before the Trips starts. After this modification, again Notification with Car + Driver Details goes to Corporate User, Corporate Admin, Digi-Go Admin & Driver
When Vendor Cancels the Trip, Notification goes to Digigo Admin Only.
Trip Journey
User, Vendor & Digigo Admin (No SMS) gets notification when Driver starts trip from Garage
Vendor & Digigo Admin (No SMS) gets notification and status update on Trip details page when Trip Code is Shared by User to Driver & Trip Starts.
Vendor can track the trip on Mobile App
Vendor & Digigo Admin (No SMS) gets notification when Trip Ends
Save Trip Details & Tracking Route for Future use. Display the Trip details on demand when clicked on a Trip
Reporting System
List of all Invoices raised so far by Digigo. Filter all these invoices by Date, Car, Driver, Paid/Unpaid, Origin City.
Settlement Report (Date, Car, Driver, Paid/Unpaid)
Trip Report (Date, Car, Driver, Status: Completed, Cancelled)
Earning Report
Requirement Analysis, Database & System Architecture
BRD, FSD Documentation
Graphic Design of Mobile App (Two options)
Total Development Efforts (In Person Days)

## Driver-Mobile App
Driver Mobile App Features
Feature Item | Efforts | Status
System Security
Login Screen
Signup Screen
OTP Validation
Forgot Password
Driver Screens
DriverDashboard New Ride, Rides completed, Rides Cancelled Assumption is to develop a very simple Dashboard
Driver Menubar
When Vendor accept the trip and assigns the Trip to Driver, Driver gets the Notification of User details, pick up location
When Admin Rejects the Vendor Trips, Vendor and Driver gets the Notifications
Trip Journey
Driver starts trip from Garage, upload his Dashboard meter reading. Photo from mobile app. Also Add the Trip start KM reading in mobile form.
Connection with Native Camera, with Delete/Cancel Option and Upload to App. Can't upload any pic from camera Roll
Trip Live tracking Starts from this point in bacground. Driver will be shifted to Google Maps Directions.
Driver Marks Reached to Pick Up Point, by pressing a button of "Reached Pickup Point"
Before starting the Trip, OTP is to shared to identify Driver.
After reached the drop off point, Get Trip END OTP from user. Enter End Trip KM reading and then press the button for "Trip Ended".
Feedback form to be shown for Driver for User
Expense Screen Enter Toll Ticket Cost & Document Proof. Parking Tickets & Document Proof.
Generate Bill Button => Notification goes to Admin & Vendor. Admin Backoffice will veerify the documents and then generate the bill.
Lists of Driver Trip Journies
List of Upcoming Journies of Driver
List of Past Journies
List of Feedback Remarks coming from User
Journey Tracking Details with Google Map
Driver Profile
After Regular Signup form, Show Driver Profile Form.
Upload KYC Documents
Create a Profile Page. Also show the Status of Documents.
Edit Profile Page
Graphics Designing of Driver Mobile App using Photoshop
Requirement Analysis, Database & System Architecture
BRD, FSD Documentation
Total Development Efforts (In Person Days)
Total Testing Efforts (30% of Development Efforts)
Total Project Management Efforts (25% of Development + Testing Efforts)
Grand Total (Person Days)
Grand Total (Person Month) (1 PM = 22 PD)